## Estimated Costs
PROGRESS VERSUS COST
Progress made versus the cost spent over time. If % Complete line below the cumulative cost line,your project may be over budget.
COST STATUS
-
COST STATUS
Try setting as baseline
COST OVERVIEW
Cost status for top level tasks.
Cost status for all top-level tasks. Is your baseline zero?

## Estimated Cash Flow
Cash Flow
The chart shows the project's cumulative cost and the cost per quater.
To see the costs for a different time period, select the Edit option from the Field List.
The table below shows cost information for all top-level tasks.
To see cost stats for all tasks, set the Outline Level in the Field List.

## Estimated Resources
Estimado |  |  |  | Real
Name | Standard Rate | Cost | Work | Name | Standard Rate | Cost | Work
Project Manager | $200.00/hour | 27153.33 | 135.77 | Project Manager | $200.00/hour | 26953.33 | 134.77
Analista Funcional | $140.00/hour | 20948.67 | 149.63 | Analista Funcional | $140.00/hour | 20948.67 | 149.63
Diseñador | $120.00/hour | 29448 | 245.4 | Diseñador | $120.00/hour | 10248 | 85.4
Desarrollador Senior .NET | $135.00/hour | 161730 | 1198 | Desarrollador Senior .NET | $135.00/hour | 205875 | 1525
Desarrollador Junior .NET | $60.00/hour | 69934 | 1165.57 | Desarrollador Junior .NET | $60.00/hour | 87899.85 | 1465
DBA | $80.00/hour | 7232 | 90.4 | DBA | $80.00/hour | 7552 | 94.4
Tester | $110.00/hour | 92224 | 838.4 | Tester | $110.00/hour | 130834 | 1189.4
Diseñador Grafico | $110.00/hour | 52800 | 480 | Diseñador Grafico | $110.00/hour | 9480.17 | 86.18
Data Entry | $0.00/hour | 400 | 6 | Data Entry | $0.00/hour | 400 | 6

## Costs
Name | Cost | Baseline Cost | Cost Variance | Duration | Baseline Duration | Duration Variance
Planificación | 4347 | 4347 | 0 | 24 hours | 24 hours | 0 hours
Requerimientos | 14786 | 14786 | 0 | 57 hours | 57 hours | 0 hours
Análisis | 10144.33 | 10144.33 | 0 | 43 hours | 43 hours | 0 hours
Diseño | 18530 | 18530 | 0 | 82 hours | 82 hours | 0 hours
Codificacion y prueba unitaria | 367800 | 366600 | 1200 | 1348 hours | 1108 hours | 240 hours
Prueba integral | 36330 | 36330 | 0 | 93 hours | 74 hours | 19 hours
Implementación | 3418 | 3418 | 0 | 47 hours | 22 hours | 25 hours
Validaciones y Test de Aceptacion | 39531.17 | 2410 | 37121.17 | 115 hours | 92 hours | 23 hours
Cierre del Proyecto | 1600 | 1600 | 0 | 8 hours | 8 hours | 0 hours
Capacitacion | 2284.51 | 2284.51 | 0 | 16 hours | 16 hours | 0 hours
Mantenimiento | 1420 | 1420 | 0 | 7 hours | 7 hours | 0 hours
PROGRESS VERSUS COST
Progress made versus the cost spent over time. If % Complete line below the cumulative cost line,your project may be over budget.
COST STATUS
-
COST ATUS
Try setting as baseline
COST OVERVIEW
Cost status for top level tasks.
Cost status for all top-level tasks. Is your baseline zero?

## Burndown
-
Burndown
Work Burndown
Shows how much work you have completed and how much you have left. If the remaining cumulative work line is steeper, then the project may be late. Is your baseline zero?
Task Burndown
Shows how many tasks you have completed and how many you have left. If the remaining tasks line is steeper, then your project may be late.
Try setting a baseline
Learn more

## Cash Flow
Cash Flow

## Acumulado Comparacion
Tarea | Duracion Real (hs) | Duracion Estimada (hs) | Desvio | Costo Real | Acumulado Real | Costo Estimado | Column1 | Acumulado Estimado
Total | 1822 | 1523 | 16.41% | 500191.01 |  | 461870 | 7.661%
Planificación | 24 | 24 | 0% | 4347 | 4347 | 4347 | 0% | 4347
Requerimientos | 57 | 57 | 0% | 14786 | 19133 | 14786 | 0% | 19133
Análisis | 43 | 43 | 0% | 10144.33 | 29277.33 | 10144.33 | 0% | 29277.33
Diseño | 82 | 82 | 0% | 18530 | 47807.33 | 18530 | 0% | 47807.33
Codificacion y prueba unitaria | 1348 | 1108 | 17.8% | 367800 | 415607.33 | 366600 | 0.3263% | 414407.33
Prueba integral | 93 | 74 | 20.43% | 36330 | 451937.33 | 36330 | 0% | 450737.33
Implementación | 47 | 30 | 36.17% | 3418 | 455355.33 | 3418 | 0% | 454155.33
Validaciones y Test de Aceptacion | 115 | 92 | 20% | 39531.17 | 494886.5 | 2410 | 93.9% | 456565.33
Cierre del Proyecto | 8 | 8 | 0% | 1600 | 496486.5 | 1600 | 0% | 458165.33
Capacitacion | 16 | 16 | 0% | 2284.51 | 498771.01 | 2284.67 | -0.007004% | 460450
Mantenimiento | 7 | 7 | 0% | 1420 | 500191.01 | 1420 | 0% | 461870

## Cambios
500191.01 |  | 41481.17
Name | Cost | Baseline Cost | Cost Variance | Variacion | Duration | Baseline Duration | Duration Variance | Variacion Duracion (%) | Impacto en la Etapa | Impacto en Proyecto | Pad Etapa | Pad Proyecto
Usuario y Login | 760 | 760 | 0 | 0% | 2 | 2 | 0 | 0% | 1.832% | 0.1519%
Seguridad Param | 1890 | 1620 | 270 | 14.29% | 14 | 12 | 2 | 14.29% | 4.556% | 0.3779%
Habilitar/Deshabilitar Varios | 1960 | 1960 | 0 | 0% | 8 | 8 | 0 | 0% | 4.725% | 0.3919%
Achicar espacio en tablas | 1020 | 170 | 850 | 83.33% | 6 | 1 | 5 | 83.33% | 2.459% | 0.2039%
Ruta del Menu | 540 | 540 | 0 | 0% | 4 | 4 | 0 | 0% | 1.302% | 0.108%
Logos | 680 | 340 | 340 | 50% | 4 | 2 | 2 | 50% | 1.639% | 0.1359%
Refresh | 17 | 170 | -153 | -90% | 0.1 | 1 | -0.9 | -90% | 0.04098% | 0.003399%
Achicar Titulos | 340 | 340 | 0 | 0% | 2 | 2 | 0 | 0% | 0.8196% | 0.06797%
Cambiar Workflow Usuarios | 1220 | 4880 | -3660 | -75% | 4 | 16 | -12 | -75% | 2.941% | 0.2439%
Revision de Acentos | 480 | 480 | 0 | 0% | 8 | 8 | 0 | 0% | 1.157% | 0.09596%
Carga de Datos en BD | 560 | 560 | 0 | 0% | 4 | 4 | 0 | 0% | 1.35% | 0.112%
Tamano de col reajustable | 2450 | 1960 | 490 | 20% | 10 | 8 | 2 | 20% | 5.906% | 0.4898%
No se mueva la tabla con el mensaje | 14.17 | 1360 | -1345.83 | -98.96% | 0.083333 | 8 | -7.9167 | -98.96% | 0.03416% | 0.002833%
Menu Anclable | 440 | 0 | 440 | 100% | 4 | 0 | 4 | 100% | 1.061% | 0.08797%
Testing 1 | 6160 | 6160 | 0 | 0% | 56 | 56 | 0 | 0% | 14.85% | 1.232%
ABM de CD | 760 | 760 | 0 | 0% | 2 | 2 | 0 | 0% | 1.832% | 0.1519%
Ensanchar forms | 1960 | 1960 | 0 | 0% | 8 | 8 | 0 | 0% | 4.725% | 0.3919%
Corregir % | 60 | 240 | -180 | -75% | 1 | 4 | -3 | -75% | 0.1446% | 0.012%
Corregir decimales | 10 | 120 | -110 | -91.67% | 0.16667 | 2 | -1.8333 | -91.67% | 0.02411% | 0.001999%
Justificar nros a la derecha | 2450 | 3920 | -1470 | -37.5% | 10 | 16 | -6 | -37.5% | 5.906% | 0.4898%
Unidades de medicion visibles | 5 | 120 | -115 | -95.83% | 0.083333 | 2 | -1.9167 | -95.83% | 0.01205% | 0.0009996%
Seguridad por Valor | 9150 | 9150 | 0 | 0% | 30 | 30 | 0 | 0% | 22.06% | 1.829%
Single Sign-On | 1950 | 6240 | 1950 | -68.75% | 10 | 32 | -22 | -68.75% | 4.701% | 0.3899%
Testing 2 | 6160 | 6160 | 6160 | 0% | 56 | 56 | 0 | 0% | 14.85% | 1.232%
Ultima Presentacion | 445 | 445 | 0 | 0% | 1 | 1 | 0 | 0% | 1.073% | 0.08897%
100%